## Project Tracker
Project Name | Project Manager | Project Deliverable | Scope Statement | Start Date | End Date | Overall Progress
Brick Breaker Game | Samyuktha Jeevananthan | Fully functional, multi-level Brick | Develop and present a | 2025-10-20 | 2025-11-17 | 0%
|  | Breaker game with scoring, power | Python-based Brick Breaker
|  | ups, and documentation | game with advanced features
Task Name | Assigned To | Start Date | End Date | Duration (days) | Status | Comments
Set Up Pygame Environment | Josue Argueta | 2025-10-20 | 2025-10-21 | 2 | Complete | Environment configured successfully
Create Paddle and Ball Classes | Ryan Yang | 2025-10-21 | 2025-10-23 | 3 | Complete | Core movement and collisions functional
Implement Brick Layout and Collision | Samyuktha Jeevananthan | 2025-10-23 | 2025-10-25 | 3 | Complete | Brick collisions working
Add Start Menu and Difficulty Settings | Josue Argueta | 2025-10-26 | 2025-10-28 | 3 | In Progress | Adjusting ball speed per difficulty
Implement Scoring and High Score Tracking | Ryan Yang | 2025-10-27 | 2025-10-30 | 4 | In Progress | Basic scoring logic done
Create Multiple Level Layouts | Samyuktha Jeevananthan | 2025-10-30 | 2025-11-02 | 4 | Not Started | Design unique brick patterns
Add Visual and Audio Feedback | Josue Argueta | 2025-11-02 | 2025-11-04 | 3 | Not Started | Sound effects and visual flashes planned
Enhance Controls (Keyboard/Mouse) and Pause Feature | Ryan Yang | 2025-11-04 | 2025-11-06 | 3 | Not Started | Implementing pause logic
Implement Power-Ups (Wide Paddle, Multi-Ball) | Samyuktha Jeevananthan | 2025-11-06 | 2025-11-09 | 4 | Not Started | Add temporary paddle effects
Code Optimization and Debugging | Ryan Yang | 2025-11-09 | 2025-11-11 | 3 | Not Started | Refactor collisions
Gameplay Testing | Josue Argueta | 2025-11-11 | 2025-11-13 | 3 | Not Started | User testing planned
Documentation and README Creation | Samyuktha Jeevananthan | 2025-11-13 | 2025-11-14 | 2 | Not Started | Include setup and control info
Demo Video Recording | Ryan Yang | 2025-11-14 | 2025-11-16 | 3 | Not Started | Short video showing key features
Final Submission Preparation | Team | 2025-11-16 | 2025-11-17 | 2 | Not Started | Finalize report and files